## Sheet1
Commercial Bid Evaluation
Client Name: |  | Crescent Point Energy Corp
Project Name: |  | Internal Engineering
Material / Service Description: |  | Free Water Knock Out |  |  | Bidder No. 1 |  | Bidder No. 2 |  | Bidder No. 3 |  | Bidder No. 4 |  | Bidder No. 5
SWAT Ref No.: |  | 15-010-001 | Bidder Name: |  | Cameron |  | Compass Compression |  | Evolution |  | Foremost |  | Oilpro
AFE: |  | ? | Bid Number: |  | OP-151125600 |  | 1511-353 |  | EV152-74 |  | Q00-002663 |  | 12477
RAS Date: |  | ? | Contact Person: |  | Terry Murtagh |  | Marty Holzinger |  | Garth Gazdewich |  | Monte Scott |  | Olav Cramer
Evaluated By: |  | Nick Crowston | Contact Number: |  | 1-403-203-2138 |  | 403-570-5962 |  | 403-604-4457 |  | 403-287-6990 |  | 403-215-3373
Evaluation Date: |  | 2015-11-18 | Submission Date: |  | 2015-11-17 |  | 2015-11-17 |  | 2015-11-17 |  | 2015-11-17 |  | 2015-11-17
Bid Totals and Priority Commercial Information
|  | Total Value of Requested Materials / Services: |  |  | 974252 |  | 656600 |  | 485900 |  | 815325 |  | 610200
|  | Total Value of Required Options: |  |  | 0 |  | 3500 |  | 69565 |  | 0 |  | 27400
|  | Total Value Material / Services and Options: |  |  | 974252 |  | 660100 |  | 555465 |  | 815325 |  | 637600
|  | Bid Currency: |  |  | CAD$ |  | CAD$ |  | CAD$ |  | CAD$ |  | CAD$
|  | Conversion Rate at Date of Evaluation: |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  | Total Bid Value w/ Options Converted to CDN$: |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  | Bid Validity (in days): |  |  | 30 |  | 30 |  | 14 |  | 30 |  | 60
|  | Bid Valid Until: |  |  | 2015-12-17 |  | 2015-12-17 |  | 2015-12-01 |  | 2015-12-17 |  | 2016-01-16
|  | Estimated Lead Time to Delivery: |  |  | 38 Weeks ARO |  | 20-22 Weeks ARO |  | 10-11 Weeks ARO |  | 24 Weeks ARO |  | 19 Weeks ARO
|  | Incoterms |  |  | FCA |  | Exworks |  | FOB |  | Exworks |  | Exworks
|  | Shipping / Pick Up Location |  |  | 0 |  | Compass Calgary Facility |  | Edmonton, AB |  | Lloydminster, AB |  | Halkirk, AB
|  | Technically Acceptable (Yes or No) |  |  | 0 |  | 0 |  | Yes |  | 0 |  | 0
Commercial Recommendation
Based upon commercial and technical evaluation it is our recommendation to purchase the required FWKO package from Evolution. Please note that we recommend purchasing the additional items resulting from bid conditioning and recommended options as detailed below.
Approvals
|  | Procurement Approval |  |  | Projects Approval |  |  |  | Client Approval
|  | Name: |  |  | Name: |  |  |  | Name:
|  | Date: |  |  | Date: |  |  |  | Date:
|  | Signature: |  |  | Signature: |  |  |  | Signature:
[5 empty] | Bidder No. 1 |  | Bidder No. 2 |  | Bidder No. 3 |  | Bidder No. 4 |  | Bidder No. 5
|  |  | Bidder Name: |  | Cameron |  | Compass Compression |  | Evolution |  | Foremost |  | Oilpro
Detailed Item Pricing as per Tender Pricing Document
Item No. | Tag No. | Description of Material or Service | Qty | UofM | Unit Price | Total Price | Unit Price | Total Price | Unit Price | Total Price | Unit Price | Total Price | Unit Price | Total Price
1 |  | 10’ x 50’ FWKO Package | 1 | EA | 974252 | 974252 | 0 | 0 | 439760 | 439760 | 815325 | 815325 | 610200 | 610200
2 |  | 8’ x 30’ FWKO Package | 0 | EA | 884997 | 0 | 0 | 0 | 384200 | 0 | 0 | 0 | 482400 | 0
3 |  | Compass Compression Services Ltd. sour crude oil Heated FWKO package consisting of: • Horizontal 3 Phase Heated FWKO vessel 96” ID x 40’-0” s/s • One 24” OD firetube, 2.5 MMBTU/hr duty • Desanding system for full vessel length • Structural steel skid base • Self-framing building • Process piping, valves and controls • Burner, BMS, and fuel gas train • Painting and insulation • Inspection and documentation | 1 | EA | 0 | 0 | 656600 | 656600 | 0 | 0 | 0 | 0 | 0 | 0
Cost Adders resulting from bid conditioning clarifications
4 |  | Electrical quote, 8’0” x 30’0” S/S Sour FWKO Package INCLUDES: Electrical installation as per associated drawings Instrumentation installation as per associated P&ID drawings Instrumentation installation for owner supplied material & equipment Supply and install of conduit, fittings and conductors (Class 1 Zone 2) Supply and install of AIT/AE-2100 & AIT/AE-2101 (Net Safety H2S & Net Safety LEL detectors) Function testing of all the instruments Point to point testing and verification of all 3rd Party Electrical Contractors installed devices Pre-commissioning Electrical Permit | 0 | Lot | 0 | 0 | 0 | 0 | 15000 | 15000 | 0 | 0 | 0 | 0
5 |  | Skid, P.Eng stamped by a Professional Engineer registered in Saskatchewan | 1 | EA | 0 | 0 | 0 | 0 | 1120 | 1120 | 0 | 0 | 0 | 0
6 |  | Linelist / P&ID P.Eng stamped by a Professional Engineer registered in Saskatchewan | 1 | EA | 0 | 0 | 0 | 0 | 1320 | 1320 | 0 | 0 | 0 | 0
7 |  | Building P.Eng stamped by a Professional Engineer registered in Saskatchewan | 1 | EA | 0 | 0 | 0 | 0 | 990 | 990 | 0 | 0 | 0 | 0
8 |  | Cost adder option for Mineral Wool Insulation for 8’x30’ FWKO | 0 | EA | 0 | 0 | 0 | 0 | 1155 | 0 | 0 | 0 | 0 | 0
9 |  | Cost adder option for Mineral Wool Insulation for 10’x50’ FWKO | 1 | EA | 0 | 0 | 0 | 0 | 1875 | 1875 | 0 | 0 | 0 | 0
10 |  | Cost adder of to PWHT the piping | 1 | EA | 0 | 0 | 0 | 0 | 1055 | 1055 | 0 | 0 | 0 | 0
11 |  | Cost adder to internally coat the manual valves on the water line | 1 | EA | 0 | 0 | 0 | 0 | 11200 | 11200 | 0 | 0 | 0 | 0
12 |  | cost deduct of: $260.00, using 1005E Norriseal electric level switch | 1 | EA | 0 | 0 | 0 | 0 | -260 | -260 | 0 | 0 | 0 | 0
13 |  | cost deduct of: $3,135.00, using Rosemount 5301 Guided Wave Radar Level Transmitter | 1 | EA | 0 | 0 | 0 | 0 | -3135 | -3135 | 0 | 0 | 0 | 0
14 |  | change to CCS 6900GZE16 (18 to 150psi increasing), same cost | 1 | EA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 |  | Cost adder to go with ZEDI EFM: $9,595.00 | 1 | EA | 0 | 0 | 0 | 0 | 9595 | 9595 | 0 | 0 | 0 | 0
16 |  | Cost deduct of $12,570.00 to change gas outlet from 6” to 4”, includes, meter run, ball valve, BPCV and fittings/pipe | 1 | EA | 0 | 0 | 0 | 0 | -12570 | -12570 | 0 | 0 | 0 | 0
17 |  | Cost adder of $17,215.00 to go with V500 Level Control Valves on water and Condy lines | 1 | EA | 0 | 0 | 0 | 0 | 17215 | 17215 | 0 | 0 | 0 | 0
18 |  | Cost adder of $2,735.00 to add roots meter | 1 | EA | 0 | 0 | 0 | 0 | 2735 | 2735 | 0 | 0 | 0 | 0
19 |  | To replace the 3 pen chart recorder with a Nuflo Scanner 2000EFM will be: $2,485.00 | 0 | EA | 0 | 0 | 0 | 0 | 2485 | 0 | 0 | 0 | 0 | 0
|  | Total Value of Requested Materials / Services: |  |  | 974252 |  | 656600 |  | 485900 |  | 815325 |  | 610200
Recommended Options - Detailed Item Pricing
Item No. | Tag No. | Description of Material or Service | Qty | UofM | Unit Price | Total Price | Unit Price | Total Price | Unit Price | Total Price | Unit Price | Total Price | Unit Price | Total Price
Opt 1 |  | 36” OD x 4’-0” s/s flanged gas dome (required only for gas rate >3.0 MMscf/day) |  | EA | 0 | 0 | 27700 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Opt 2 |  | Kenilworth burners and fuel gas trains - TBD |  | EA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Opt 3 |  | Internal desand manifolds and sand-pans 316 Stainless steel construction for heating section (Included) |  | EA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Opt 4 |  | Optional 316 Stainless steel materials for external de-sand water piping - TBD |  | EA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Opt 5 |  | Optional removable zinc (3”x 44”) anodes c/w insulating roller and grounding pigtail including 4” 150# RFLWN nozzle and blind | 1 | EA | 0 | 0 | 3500 | 3500 | 0 | 0 | 0 | 0 | 0 | 0
Opt 6 |  | Internally coat 8’x30’ FWKO w/ 10-12 mills Devoe 253 |  |  | 0 | 0 | 0 | 0 | 28000 | 0 | 0 | 0 | 0 | 0
Opt 7 |  | Internally coat 10’x50’ FWKO w/ 10-12 mills Devoe 253 | 1 |  | 0 | 0 | 0 | 0 | 41895 | 41895 | 0 | 0 | 0 | 0
Opt 8 |  | Change ACL BMS to Profire BMS | 1 |  | 0 | 0 | 0 | 0 | 4555 | 4555 | 0 | 0 | 0 | 0
Opt 9 |  | Change ACL BMS to Kenilworth Heater Module | 1 |  | 0 | 0 | 0 | 0 | 19895 | 19895 | 0 | 0 | 0 | 0
Opt 10 |  | Profile Modbus card | 1 |  | 0 | 0 | 0 | 0 | 425 | 425 | 0 | 0 | 0 | 0
Opt 11 |  | Axiomatic 12VDC – 24VDC convertor | 1 |  | 0 | 0 | 0 | 0 | 435 | 435 | 0 | 0 | 0 | 0
Opt 11 |  | 120 VAC Electric Heat Trace Package Internal valvetrain heat trace installed External junction Box for field connection |  |  | 0 | 0 | 0 | 0 | 750 | 0 | 0 | 0 | 0 | 0
Opt 12 |  | Full Length Eavestrough c/w (2) Downspouts | 1 |  | 0 | 0 | 0 | 0 | 915 | 915 | 0 | 0 | 0 | 0
Opt 13 |  | 6” Full Length Ridge vent | 1 |  | 0 | 0 | 0 | 0 | 1445 | 1445 | 0 | 0 | 0 | 0
Opt 14 |  | To Provide Electrical Package Class 1 Div2 as per drawing xxxxx-B-4-12 | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27400 | 27400
Opt 15 |  | To Provide Spare Firetube for 8' x 30' FWKO |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45500 | 0
Opt 16 |  | To Provide Spare Firetube for 10' x 50' FWKO |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49500 | 0
Opt 17 |  | Freight to site for 8' x 30' FWKO |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15450 | 0
Opt 18 |  | Freight to site for 10' x 50' FWKO |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 46845 | 0 | 22250 | 0
|  | Total Value of Required Options: |  |  | 0 |  | 3500 |  | 69565 |  | 0 |  | 27400
Commercial Terms and Conditions
[5 empty] | Bidder No. 1 |  | Bidder No. 2 |  | Bidder No. 3 |  | Bidder No. 4 |  | Bidder No. 5
|  |  | Bidder Name: |  | Cameron |  | Compass Compression |  | Evolution |  | Foremost |  | Oilpro
|  | Bid Validity (Days) |  |  | 30 |  | 30 |  | 14 |  | 30 |  | 60
|  | Bid Valid Until |  |  | 2015-12-17 |  | 2015-12-17 |  | 2015-12-01 |  | 2015-12-17 |  | 2016-01-16
|  | Currency |  |  | CAD$ |  | CAD$ |  | CAD$ |  | CAD$ |  | CAD$
|  | Taxes |  |  | Extra |  | Extra |  | Extra |  | Extra |  | Extra
|  | Price Escalation |  |  | Price escalation will not be allowed post award and a change order process will be used for this order. Due to the volatility of steel prices at the present time, Cameron reserves the right to review material cost at time of order. |  | Price escalation will not be allowed post award and a change order process will be used for this order. |  | Vendor acknowledged price escalation will not be allowed post award and a change order process will be used for this order. |  | Price escalation will not be allowed post award and a change order process will be used for this order. |  | Price escalation will not be allowed post award and a change order process will be used for this order.
|  | Billing Process (If Applicable) |  |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
|  | Estimate Accuracy (If Applicable) |  |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
|  | Estimated Lead Time |  |  | 26 - 30 Weeks ARAD |  | 20-22 Weeks ARO |  | 8-9 Weeks ARAD |  | 20 Weeks ARAD |  | 17 Weeks ARAD
|  | Drawing Approval Time (If Lead Time is ARAD) |  |  | 8 Weeks ARO |  | 2-4 Weeks ARO |  | Est. 2 weeks ARO |  | 4 Weeks ARO |  | Est. 2 weeks ARO
|  | Actual Est. Lead Time (ARAD Plus Drawing Approval or ARO) |  |  | 38 Weeks ARO |  | 20-22 Weeks ARO |  | 10-11 Weeks ARO |  | 24 Weeks ARO |  | 19 Weeks ARO
|  | Incoterms |  |  | FCA |  | Exworks |  | FOB |  | Exworks |  | Exworks
|  | Shipping / Pick Up Location |  |  |  |  | Compass Calgary Facility |  | Edmonton, AB |  | Lloydminster, AB |  | Halkirk, AB
Shipping Weight and Dimensions
|  | Travel and Expenses (If Applicable) |  |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A
|  | VDDR Documentation Included |  |  | Marked up VDDR Included with bid |  |  |  | Marked up VDDR was requested but not provided. |  | Marked up VDDR Included with bid
|  | Additional Costs for Documentation |  |  | Price includes one set of drawings and one set of minor revisions to those drawings |  | Includes: (2) Hard copy and (1) CD copy will be provided and will include the following; - Index - Unit build sheet - Unit Drawings, including PID and GA as-built drawings - Skid / recommended pile locations and building drawings - Bill of Materials, as built - PSV test reports - Instrumentation vendor literature - QC documentation - Vessel U-1A’s or AB-25’s and nameplate facsimiles - Process pipe ABSA AB-83 and BCSA Form 1330 (for BC installations) - Process pipe line list - ABSA AB-10 report - Quality Assurance Assembly Report |  | One(1) set of QC/Operating Manuals is included in the given price. |  | All documents, drawings, and explanatory notes to be provided in one (1) hard copy. |  | One (1) C.D. and one (1) paper copy with operating manual and quality control manual information is included with the given price.
|  | Payment Terms |  |  | 20% Upon written order acceptance by Cameron 25% Upon order of FWKO 20% Upon submittal of P&ID’s to Customer for approval 25% Upon hydrotest of the FWKO 10% Upon notification of readiness to ship Net30 Days |  | 20% on receipt of order 25% on receipt of vessel heads and shells 20% on order of controls and instruments 20% on vessel hydrotest 15% on substantial completion Net45 Days |  | 50% upon receipt of purchase order 50% upon notification of readiness to ship Net30 Days |  | 15% on Award 15% on First General Arrangement Drawing Submission 30% on Order of Shell and Heads 30% on Completion of Hydrotest 10% on Ready to Ship Net30 Days |  | 25% invoiced on order/Receipt of Purchase Order 25% on receipt of major materials 25% on Approval of Drawings 25% on completion in yard and prior to shipment Net45 Days
|  | Cancelation Terms |  |  | After receipt of customer’s PO - 10% of contract value After submission of 1st set of drawings - 30% of contract value After purchase order placed for heads & shells - 50% of contract value After purchase order placed for BMS - 70% of contract value After notification of above items being shipped to place of manufacture - 90% of contract value After receipt of above items at place of manufacture - 100% of contract value |  |  |  | Cancellation before material ordered/drawings approved: No charge Cancellation upon order/receipt of material: 25% of total cost Cancellation upon completion of the construction of the vessel, piping and skid: 100% of total cost |  | 15% of Total Contract Value After Award but Prior to 1st Drawing Submission 30% of Total Contract Value After Ordering Major Materials but Prior to Receipt 90% of Total Contract Value After Start of Construction 100% of Total Contract Value After Mechanical Completion
|  | Warranty |  |  | Parts manufactured by Cameron that fail through normal use or operation within twelve (12) months from the date of start-up or eighteen (18) months from the date of shipment, whichever occurs first, will be repaired or replaced F.O.B. point of origin. Parts that become defective due to inattention lack of lubrication, or normal wear, will be the purchaser’s responsibility. Equipment such as pumps, motors, coatings, electrical controls, etc., will carry only the warranty assumed by the original manufacturer. Cameron makes no warranty beyond the warranty of the original component manufacturer. The O.E.M. will be solely responsible for determining the validity of warranty claims. |  | Warranty Regarding Work (a) Compass standard warranty period of eighteen (18) months from offer to ship or twelve (12) months from start-up, whichever occurs first has been offered. |  | All equipment supplied by Evolution Production Equipment will be guaranteed to be free of manufacturing defects for twelve (12) months from completion. |  | Foremost Universal LP warrants parts and labour relating to the products hereunder against defects in materials and workmanship for a period which expires the earliest of: (a) eighteen (18) months from the date of manufacture; or (b) twelve (12) months from the commissioning of such products. |  | All equipment fabricated for OilPro by Cape Manufacturing Ltd will be guaranteed to be free of manufacturing defects for eighteen (18) months from completion or twelve (12) months from commissioning, whichever is less. In order to maintain warranty, Cape must be notified immediately in the event of operational problems. No process guarantee is provided on this equipment.
|  | Terms & Conditions |  |  | As per Camerons T's & C's |  | As per Compass T's & C's |  | As per CP T's&C's |  | As per Formost T's & C's |  | As per Oil Pro T's & C's
|  | Technically Acceptable (Yes or No) | [6 empty] | Yes
Notes / Comments
Cameron |  | Notes / Comments
Compass Compression |  | Notes / Comments
Compass quoted only an 8' x 40' FWKO which was not a requested size option. Compass provided the same options for FWKO & Treater, not sure if these actually apply to both bids.
Evolution |  | Notes / Comments
Evolution quoted faster delivery for 8' x 30' FWKO: 5-6 Weeks ARAD, confirmed that they can provide up to 6 months of free storage, from equipment ready to ship date.
Foremost |  | Notes / Comments
Foremost did not provide a quote for an 8' x 30' FWKO option
Oilpro |  | Notes / Comments
Oil pro quoted faster delivery for 8' x 30' FWKO: 13 - 14 Weeks ARAD
Formulas:
Bidder No. 1 = F13+[Bidder No. 1, row above]
Bidder No. 2 = H13+[Bidder No. 2, row above]
Bidder No. 3 = J13+[Bidder No. 3, row above]
Bidder No. 4 = L13+[Bidder No. 4, row above]
Bidder No. 5 = N13+[Bidder No. 5, row above]